## Sheet1
Task ID | Task Name | Duration | Predecessors
1 | Mechanical calculation and GA drawing Submission by USPL | 3
2 | Mechanical calculation and GA drawing Approval by Client | 1 | 1
3 | Detail drawing Submission by USPL | 3
4 | Detail drawing Approval by Client | 1 | 3
5 | QA documents Submission by USPL | 8
6 | QA documents Approval by Client | 7 | 5
7 | Plates | 28 | 2
8 | Dish head - 4 units | 50 | 2
9 | Nozzle pipe, Flange & Fittings | 28 | 4
10 | Supports | 28 | 4
11 | Gasket, Bolt nuts & Others | 45 | 4
12 | Material Inspection | 2 | 7
13 | Material preparation for shell & shell parts | 3 | 6,12
14 | Shell / Pad rolling | 8 | 13
15 | Long seam welding | 8 | 14
16 | Cir seam fitup & welding | 8 | 15
17 | Nozzle prefabrication | 10 | 14,9
18 | Shell with 1st dished head fitup & welding | 8 | 16,8
19 | Nozzle fitup & welding | 8 | 17,18
20 | Shell with 2nd dished head fitup & welding | 8 | 19
21 | Supports fitup & welding | 8 | 10,20
22 | NDE | 3 | 21
23 | Final dimension & Visual inspection - USPL | 4 | 22
24 | Hydro test - USPL | 10 | 23
25 | Blasting & Painting | 14 | 24
26 | Ready for Collection | 2 | 25